## Joe Tracker
Team Tracking Sheet
Team 3 | TEAM socl
Team Lead | Zane Coppedge
Date | 2014-03-14
Major Artifacts | Est % complete | Comments
Use Case Scenarios | 100% | Submitted to Joe for Review
Use Case Specifications | 100% | Submitted to Joe for Review
Technical (Functional)Specs | 100% | Submitted to Joe for Review
CRC cards | 90%
Code Assignments | 100% | Zane Ryen / Frontend--Kelly Bryan Simran / Backend
Code Status by Area | Est % complete | Comments
By Area
Database handler | 70%
E-mail handler | 90%
User Interface | 70%
Main System | 82%
Code Status by Engineer | Est % complete | Comments
Zane | 70% | Frontend
Ryen | 70% | Frontend
Kelly | 60% | Backend
Simran | 60% | Backend
Bryan | 60% | Backend