## Joe Tracker
Team Tracking Sheet
Team 3 | TEAM socl
Team Lead | Zane Coppedge
Date | 2014-03-11
Major Artifacts | Est % complete | Comments
Use Case Scenarios | 100% | Submitted to Joe for Review
Use Case Specifications | 100% | Submitted to Joe for Review
Technical (Functional)Specs | 33% | Currently working through section 4
CRC cards | 50% | Simran currently working ECD 14 March
Code Assignments | 100% | Zane Ryen / Frontend--Kelly Bryan Simran / Backend
Code Status by Area | Est % complete | Comments
By Area
Database handler | 40% | Connection object mostly functional
E-mail handler | 20% | Concept and pseudo code complete
User Interface | 40% | At login working backwards now
Main System | 30%
Code Status by Engineer | Est % complete | Comments
Zane | 40% | Frontend
Ryen | 40% | Frontend
Kelly | 20% | Backend
Simran | 20% | Backend
Bryan | 20% | Backend

## Team Breakdown Tracker
Program (Overall) | 20% | Construct
Install Program | 0% | Install Shell | CPU with Windows
|  | Check for minimum system requirements | Minimum Memory and Hard Drive
User interface for install
Successful installation criteria
User Interface | 20% | Sign Up button-->
User inputs include:
|  | Phone | DataBase
|  | Address | DataBase
|  | Email | DataBase
|  | Emergency Contact | DataBase
|  | Privacy Option | DataBase
|  | Text Alerts Y/N | DataBase
|  | Email Alerts Y/N | DataBase
|  | Playing History | DataBase
|  | Batting Average | DataBase
|  | Positions Trained | DataBase
|  | Positions Played | DataBase
|  | Expected Availability to Play% | DataBase
|  | Team Requested to be on | DataBase
|  | Submit button--> | Stores User data in database | Sends email to coach | Coach rec email-approves team selection | Coach assigns position | Email sent back when approved and assigned
User Interface | 20% | Login Button--> |  | Edit Player Information Button-->
|  | Username | Database | Phone | DataBase
|  | Password | Database | Address | DataBase
|  | Password Hint | Database-Email | Email | DataBase
|  | Forgot Password | Database-Email | Emergency Contact | DataBase
|  | Forgot Username | Database-Email | Privacy Option | DataBase
|  |  |  | Text Alerts Y/N | DataBase
|  |  |  | Email Alerts Y/N | DataBase
|  |  |  | Playing History--> | DataBase
|  |  |  | Batting Average | DataBase
|  |  |  | Positions Trained | DataBase
|  |  |  | Positions Played | DataBase
|  |  |  | Expected Availability to Play% | DataBase
Coach- Request Info-Email-Handshake
Delete Player Button-->
|  |  |  | Delete Phone | DataBase
|  |  |  | Delete Address | DataBase
|  |  |  | Delete Email | DataBase
|  |  |  | Delete Emergency Contact | DataBase
|  |  |  | Delete Privacy Option | DataBase
|  |  |  | Delete Text Alerts Y/N | DataBase
|  |  |  | Delete Email Alerts Y/N | DataBase
|  |  |  | Playing History | DataBase
|  |  |  | Delete Batting Average | DataBase
|  |  |  | Delete Positions Trained | DataBase
|  |  |  | Delete Positions Played | DataBase
|  |  |  | Delete Expected Availability to Play% | DataBase
Database of individual deleted
Game Schedule Button-->
|  |  |  | Past Games--> | Database
|  |  |  | List of teams played and scores | Coach Inputs
|  |  |  | Future Games--> | Database
|  |  |  | Date, Time, Location, Team | Coach Inputs
Weather Check Button-->
|  |  |  | Weather Checker | Database utilizing 5 dig zip
Coach Interface | 20% | Login Button--> |  | Edit Player Information Button-->
|  | Username | Database | Phone | DataBase
|  | Password | Database | Address | DataBase
|  | Password Hint | Database-Email | Email | DataBase
|  | Forgot Password | Database-Email | Emergency Contact | DataBase
|  | Forgot Username | Database-Email | Privacy Option | DataBase
|  |  |  | Text Alerts Y/N | DataBase
|  |  |  | Email Alerts Y/N | DataBase
|  |  |  | Playing History--> | DataBase
|  |  |  | Batting Average | DataBase
|  |  |  | Positions Trained | DataBase
|  |  |  | Positions Played | DataBase
|  |  |  | Expected Availability to Play% | DataBase
Coach- Request Info-Email-Handshake
Delete Player Button-->
|  |  |  | Delete Phone | DataBase
|  |  |  | Delete Address | DataBase
|  |  |  | Delete Email | DataBase
|  |  |  | Delete Emergency Contact | DataBase
|  |  |  | Delete Privacy Option | DataBase
|  |  |  | Delete Text Alerts Y/N | DataBase
|  |  |  | Delete Email Alerts Y/N | DataBase
|  |  |  | Playing History | DataBase
|  |  |  | Delete Batting Average | DataBase
|  |  |  | Delete Positions Trained | DataBase
|  |  |  | Delete Positions Played | DataBase
|  |  |  | Delete Expected Availability to Play% | DataBase
Coach- Request Info-Email-Handshake
Game Schedule Button-->
|  |  |  | Past Games--> | Database
|  |  |  | List of teams played and scores | Coach Inputs
|  |  |  | Future Games--> | Database
|  |  |  | Date, Time, Location, Team | Coach Inputs