## Joe Tracker
Team Tracking Sheet
Team 3 | TEAM socl
Team Lead | Zane Coppedge
Date | 2014-03-14
Major Artifacts | Est % complete | Comments
Use Case Scenarios | 100% | Submitted to Joe for Review
Use Case Specifications | 100% | Submitted to Joe for Review
Technical (Functional)Specs | 100% | Submitted to Joe for Review
CRC cards | 100% | Submitted to Joe for Review
Code Assignments | 100% | Zane Ryen / Frontend--Kelly Bryan Simran / Backend
Code Status by Area | Est % complete | Comments
By Area
Database handler | 60% | Connection object mostly functional
E-mail handler | 80% | Concept and pseudo code complete
User Interface | 60% | At login working backwards now
Main System | 60%
Code Status by Engineer | Est % complete | Comments
Zane | 60% | Frontend
Ryen | 60% | Frontend
Kelly | 50% | Backend
Simran | 50% | Backend
Bryan | 50% | Backend

## Team Breakdown Tracker
Program Main | 50%
Install Program | 0% | Install Shell
Check for minimum system requirements
User interface for install
Successful installation criteria
User Interface | 60%
| Sign Up Button | User inputs include:
Phone
Address
Email
Emergency Contact
Privacy Option
Text Alerts Y/N
Email Alerts Y/N
Playing History
Batting Average
Positions Trained
Positions Played
Expected Availability to Play%
Team Requested to be on
Submit button
User Interface | 60% |  | 20%
| Login Button | Username | Edit Player Info | Phone
|  | Password |  | Address
|  | Password Hint |  | Email
|  | Forgot Password |  | Emergency Contact
|  | Forgot Username |  | Privacy Option
Text Alerts Y/N
Email Alerts Y/N
Playing History-->
Batting Average
Positions Trained
Positions Played
Expected Availability to Play%
|  |  | Delete Player Button | Delete Phone
Delete Address
Delete Email
Delete Emergency Contact
Delete Privacy Option
Delete Text Alerts Y/N
Delete Email Alerts Y/N
Playing History
Delete Batting Average
Delete Positions Trained
Delete Positions Played
Delete Expected Availability to Play%
Game Sched
Past Games-->
List of teams played and scores
Future Games-->
Date, Time, Location, Team
WX Button
Weather Checker
Coach Interface | 20%
| Login Button | Username | Edit Player Information Button | Phone
|  | Password |  | Address
|  | Password Hint |  | Email
|  | Forgot Password |  | Emergency Contact
|  | Forgot Username |  | Privacy Option
Text Alerts Y/N
Email Alerts Y/N
Playing History-->
Batting Average
Positions Trained
Positions Played
Expected Availability to Play%
|  |  | Delete Player Button | Delete Phone
Delete Address
Delete Email
Delete Emergency Contact
Delete Privacy Option
Delete Text Alerts Y/N
Delete Email Alerts Y/N
Playing History
Delete Batting Average
Delete Positions Trained
Delete Positions Played
Delete Expected Availability to Play%
|  |  | Game Schedule | Past Games-->
List of teams played and scores
Future Games-->
Date, Time, Location, Team